## Slide 1: Scrum
1

## Slide 2: Scrum in 100 words
Scrum is an agile process that allows us to focus on delivering the highest business value in the shortest time.
It allows us to rapidly and repeatedly inspect actual working software (every week to one month)
The business sets the priorities. Our teams self-manage to determine the best way to deliver the highest priority features.
Every week to a month anyone can see real working software and decide to release it as is or continue to enhance for another iteration.

## Slide 3: Scrum Characteristics
Simple and scalable
Empirical process
Short-term detailed planning with constant feedback provides simple inspect and adapt cycle
Simple techniques
And work artifacts
Requirements are captured as user stories in a list of product backlog
Progress is made in Sprints
Teams collaborating with the Product Owner
Optimizes working environment
Reduces organizational overhead
Detects everything that gets in the way of delivery
Fosters openness and demands visibility

## Slide 4: Scrum Framework
Roles: Product Owner, Scrum Master, Scrum Team
Ceremonies: Sprint Planning, Sprint Review, Sprint Retrospective, and Daily Stand-up
Artifacts: Product Backlog, Sprint Backlog, Burndown Chart

## Slide 5: Scrum Roles
Product Owner
Scrum Master
Scrum Team

## Slide 6: Product Owner
Captures Product Vision
Represents the voice of the customer
Creates initial Product Backlog
Writes customer-centric items
Helps set the direction of the product (Release Date)
Accountable for ensuring that the Team delivers value to the business (prioritize according to market value)
Responsible for:
  Product Backlog
  Prioritization

## Slide 7: Scrum Master
Combination of Coach, Fixer and Gatekeeper
Makes sure the project is progressing smoothly
Monitors the work being done
Facilitates release planning
To protect the team and keep them focused on the tasks at hand
Servant-leader

## Slide 8: Scrum Team
These are the people who build products, make estimates
Scrum recommends teams of 7 +/- 2 participants
The teams are cross-functional and self-organizing
  The Team decides who shall do what
  They inspect and adapt as the Sprint goes along
  Team members should be full-time
  Membership can change only between Sprints

## Slide 9: Scrum Ceremonies
Release Planning
Sprint Planning
Daily Stand-up
Sprint Review
Sprint Retrospective

## Slide 10: Release Planning
Occurs several days before Sprint Planning
Start with the Product Backlog items
Identify features to put into a release
Team prioritizes the features

## Slide 11: Sprint Planning
Product Owner, Team, and other Stakeholders talk through the Product Backlog Items and prioritization
Team determines how much time it has available to commit during the Sprint [Time boxed]
Team selects as much of the Product Backlog as it can commit to deliver by the end of the Sprint
  Validates commitment by breaking down the PBI into Tasks with Time Estimates
  Team decides who will do what, when; thinking through sequencing, dependencies, possible tasks trades, and so forth

## Slide 12: Daily Stand-ups
Should not last more than 15 minutes
The meeting starts precisely on time
Every team member has to answer 3 questions:
  What have I done since the last meeting?
  What will I do until the next meeting?
  What impediments do I have?
ScrumMaster will facilitate resolution of these impediments
Resolution should occur outside the Daily Stand-up itself to keep it under 15 minutes

## Slide 13: Sprint Review
Updates to the Product Owner
Plans for the next Sprint
  Changes in requirements?
Demonstration

## Slide 14: Sprint Retrospective
Team reflects on the Sprint
  What went well?
  What did not go so well?
  How can we improve?

## Slide 15: Scrum Artifacts
Product Backlog
Sprint Backlog
Defect Backlog
Sprint Burndown Chart
Release Burndown Chart

## Slide 16: Product Backlog
Contains all potential features, prioritized as an absolute ordering by Business Value
It is therefore the “What” that will be built, sorted by importance
It contains rough estimates of both business value and development effort
Those estimates help the Product Owner to gauge the timeline and, to a limited extent prioritize
A dynamic list of desired work reprioritized at the start of each Sprint

## Slide 17: Prioritization
Five factors to consider when prioritizing
The commercial or operational value of the delivered story
Degree of uncertainty – the amount and significance of learning and new knowledge gained by developing the product increment
The amount of risk removed by developing the product increment
The value of having the product increment
The cost of developing the product increment

## Slide 18: Estimations
Using story points instead of hours
Numeric sizing (1 to 10)
T-shirt sizes (XS, S, M, L, XL, XXL, XXXL)
Powers of 2 (1, 2, 4, 8, …)
The Fibonacci sequence (1, 2, 3, 5, 8, 13, 21, etc.)
Planning Poker
Basing on historical trends
The best people to make the estimates are the people who build the product

## Slide 19: Story Points
Relative measure of the size of a User Story
What matters are the relative values
The raw values we assign are unimportant
A story assigned a 2 should be twice as much as a story that is assigned a 1; it should be two-thirds of a story that is estimated as 3 story points
Estimating in story points completely separates the estimation of effort from the estimation of duration

## Slide 20: Story Points
Four factors to consider when sizing
Complexity
Uncertainty
Knowledge and experience with the domain
Knowledge and experience with the technology

## Slide 21: Sprint Backlog
A subset of the Product Backlog Items which defines the work for a Sprint
Is created only by Team Members
Each Item has its own status
Should be updated every day
If a task requires more than 16 hours, it should be broken down
Team can add or subtract items from the list. The Product Owner is not allowed to do it

## Slide 22: Defect Backlog
Track bugs separately from features in their own Defect Backlog
Any bug found relating to the feature should be dealt with immediately before marking the feature complete
Plan for 1-2 Sprints focused only on Defect Backlogs

## Slide 23: Sprint Burndown Chart
Depicts the total Sprint Backlog hours remaining per day
Shows the estimated amount to release
Ideally should burn down to zero to the end of the Sprint
Actually is not a straight line

## Slide 24: Release Burndown Chart
Will the release be done in time?
X-Axis: Sprints
Y-Axis: Amount of hours remaining
The estimated work remaining can also burn upwards

## Slide 25: Sprint
Is an iteration
  Analysis
  Design
  Implementation
  Validation
Includes 1 day of Sprint Planning 1 day of Sprint Review
Time boxed Period (1-4 weeks)
  A constant duration leads to a better rhythm
Sprints are short duration milestones
  Plan Sprint durations around how long you can commit to keeping change out of the Sprint
Product is potentially releasable after every Sprint

## Slide 26: Sprint Development and Delivery
Selecting identified tasks to complete
Completing them per the team’s definition of done
This cycle repeats until all Story Points for the Sprint are earned and/or the Sprint timebox has elapsed

## Slide 27: Potentially Shippable Product Increment
At the end of each Sprint, the Team must produce a potentially shippable product increment
  High Quality
  Tested
  Complete
  Done

## Slide 28: How to write a User Story for SCRUM
Separation of the user/customer types’ goals (previous slides)
Template:
  As a <some role>, I want <something>, so that <some value>
  Describes who wants, what wants and why in one sentence
  Examples:
      “As an end user I want to be able to upload my picture to my profile page, so that my profile page looks cool”
      “As a sales person, I want to see statistics of my performance in graphical charts, so that I monitor my performance”
      “As an administrator, I want to have database backups, so that I won’t be in big trouble if something unexpected happens”
    User story does not define any details of the implementation!
    Every user story needs a Definition of Done (acceptance criteria)

## Slide 29
29
Product Vision
Product Backlog
Sprint
Backlog
2 – 4
weeks
Sprint Planning
24 hours
Backlog Grooming
Sprint Retrospective
Sprint Review
Scrum
Code
Test
Check-in
Update the Task
Potentially Shippable* Product

## Slide 30: Definition of Done
Definition of Done (DoD) must describe exactly what “done” means
  Careful attention Must be paid when defining the DoD
  The scrum team must challenge the DoD, if necessary
  “What’s not in DoD, is not needed”
  Item is either “done” or “not done”
Example:
  Story: Picture upload
    end user can upload his/her picture from profile settings page
    picture is shown on the left upper corner of the profile page
    picture is scaled to fit the profile picture box on the profile page
Does not define any details of the implementation!

## Slide 31: The classic story of the “Pig and Chicken”

## Slide 32: Questions?
?

## Slide 33: References
Late, Mohen. “Scrum – An Introduction”
Mittal, Deepak. “Introduction to Scrum”
Srivastava, Ram. “Agile Method – Scrum”